## Start Here
PlanX · Free Project Estimation Template
Model project cost, FTE and expense before approval — every number traceable to an input.
What this is
A lightweight, formula-driven planner that mirrors how PlanX (planxpm.com) builds a defensible estimate: a single place for assumptions, phases as the spine, hours-driven FTE math, and a time-phased cost & FTE rollup by quarter. No macros, no add-ins — it works in any locked-down environment.
How to use it
1. Assumptions tab — set your hours-per-FTE, contingency %, and the loaded hourly rate for each role.
2. Phases tab — list each project's phases with start and end dates (the spine of the plan).
3. Labor tab — enter hours per role, per phase, per quarter. FTE and cost are calculated for you.
4. Expenses tab — enter travel, capital, outside services and direct purchases by quarter.
5. Summary tab — read the time-phased cost & FTE by quarter, a scenario view, and totals by project.
Cell colour legend
Blue text | Your inputs — type over these.
Yellow fill | Key assumptions to set for your organization.
Black text | Calculated — leave alone; it updates automatically.
Green text | Pulled from another tab — leave alone.
Sample data
This workbook is pre-filled with two example projects (Series 7 Coolant Pump, Series 5 Pump) so you can see it working end to end. Replace the sample rows with your own — every total re-flows automatically.
When the spreadsheet starts to strain
This template shows the shape of a defensible estimate. But a spreadsheet can't reproduce itself on demand, can't trace a total back to its assumption in one click, and will happily cost a plan that exceeds capacity. PlanX does this same job live: every number decomposes to the row behind it, optimistic / expected / pessimistic scenarios and approval baselines are built in, and it refuses to render a plan that can't happen. When this file starts to sprawl across tabs, that's the signal to try PlanX.
Get PlanX → planxpm.com
Learn more about PlanX → planxpm.com

## Assumptions
Assumptions
Everything in the model traces back to these inputs. Change a number here and the whole plan re-flows.
Global settings
Hours per FTE (annual) | 1664
Hours per FTE (quarter) | 416
Contingency % | 10%
Planning currency | USD
Roles & loaded rates
Role | Loaded Rate ($/hr)
Project Manager | 145
Design Engineer | 135
Test Engineer | 130
Quality Engineer | 125
Technician | 95
↑ Add roles in the blank rows above; the Labor tab looks up rates from this list.
Note on B5: Standard planning basis for one full-time equivalent per year. Adjust to your organization.
Note on B7: Applied to total cost on the Summary tab.

## Phases
Phases
The spine of the plan. Each project's phases with start and end dates; duration is calculated.
Project | Phase | Start | End | Duration (wks) | Notes
Series 7 Coolant Pump | Design | 2026-01-05 | 2026-03-27 | 11.5714 | Concept & detailed design
Series 7 Coolant Pump | Prototype Build | 2026-03-30 | 2026-06-19 | 11.5714 | First articles
Series 7 Coolant Pump | Validation Testing | 2026-06-22 | 2026-09-25 | 13.5714 | Design validation
Series 7 Coolant Pump | Qualification | 2026-09-28 | 2026-12-18 | 11.5714 | Formal qualification
Series 7 Coolant Pump | Production Launch | 2027-01-04 | 2027-03-26 | 11.5714 | Ramp to production
Series 5 Pump | Design Update | 2026-02-02 | 2026-04-24 | 11.5714 | Carry-over redesign
Series 5 Pump | Validation Testing | 2026-04-27 | 2026-07-31 | 13.5714 | Design validation
Series 5 Pump | Production Readiness | 2026-08-03 | 2026-10-30 | 12.5714 | Line readiness
Series 5 Pump | Field Trial | 2027-01-05 | 2027-04-30 | 16.4286 | Customer field trial

## Labor
Labor · Hours → FTE → Cost
Enter hours per role, per phase, per quarter. Rate is looked up from Assumptions; FTE and cost calculate.
Project | Phase | Role | Q1 2026 Hrs | Q2 2026 Hrs | Q3 2026 Hrs | Q4 2026 Hrs | Q1 2027 Hrs | Q2 2027 Hrs | Q3 2027 Hrs | Q4 2027 Hrs | Rate $/hr | Total Hrs | Q1 2026 $ | Q2 2026 $ | Q3 2026 $ | Q4 2026 $ | Q1 2027 $ | Q2 2027 $ | Q3 2027 $ | Q4 2027 $ | Total $
Series 7 Coolant Pump | Design | Design Engineer | 350 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 470 | 47250 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 63450
Series 7 Coolant Pump | Design | Technician | 120 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 180 | 11400 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 17100
Series 7 Coolant Pump | Prototype Build | Design Engineer | 0 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 135 | 270 | 0 | 24300 | 12150 | 0 | 0 | 0 | 0 | 0 | 36450
Series 7 Coolant Pump | Prototype Build | Technician | 0 | 260 | 180 | 0 | 0 | 0 | 0 | 0 | 95 | 440 | 0 | 24700 | 17100 | 0 | 0 | 0 | 0 | 0 | 41800
Series 7 Coolant Pump | Validation Testing | Test Engineer | 0 | 0 | 320 | 140 | 0 | 0 | 0 | 0 | 130 | 460 | 0 | 0 | 41600 | 18200 | 0 | 0 | 0 | 0 | 59800
Series 7 Coolant Pump | Validation Testing | Technician | 0 | 0 | 220 | 120 | 0 | 0 | 0 | 0 | 95 | 340 | 0 | 0 | 20900 | 11400 | 0 | 0 | 0 | 0 | 32300
Series 7 Coolant Pump | Qualification | Quality Engineer | 0 | 0 | 0 | 300 | 120 | 0 | 0 | 0 | 125 | 420 | 0 | 0 | 0 | 37500 | 15000 | 0 | 0 | 0 | 52500
Series 7 Coolant Pump | Qualification | Test Engineer | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 0 | 130 | 240 | 0 | 0 | 0 | 20800 | 10400 | 0 | 0 | 0 | 31200
Series 7 Coolant Pump | Production Launch | Design Engineer | 0 | 0 | 0 | 0 | 140 | 90 | 0 | 0 | 135 | 230 | 0 | 0 | 0 | 0 | 18900 | 12150 | 0 | 0 | 31050
Series 7 Coolant Pump | Program Mgmt | Project Manager | 90 | 90 | 90 | 90 | 80 | 60 | 0 | 0 | 145 | 500 | 13050 | 13050 | 13050 | 13050 | 11600 | 8700 | 0 | 0 | 72500
Series 5 Pump | Design Update | Design Engineer | 200 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 310 | 27000 | 14850 | 0 | 0 | 0 | 0 | 0 | 0 | 41850
Series 5 Pump | Validation Testing | Test Engineer | 0 | 180 | 220 | 0 | 0 | 0 | 0 | 0 | 130 | 400 | 0 | 23400 | 28600 | 0 | 0 | 0 | 0 | 0 | 52000
Series 5 Pump | Validation Testing | Technician | 0 | 120 | 160 | 0 | 0 | 0 | 0 | 0 | 95 | 280 | 0 | 11400 | 15200 | 0 | 0 | 0 | 0 | 0 | 26600
Series 5 Pump | Production Readiness | Quality Engineer | 0 | 0 | 120 | 180 | 0 | 0 | 0 | 0 | 125 | 300 | 0 | 0 | 15000 | 22500 | 0 | 0 | 0 | 0 | 37500
Series 5 Pump | Field Trial | Test Engineer | 0 | 0 | 0 | 0 | 90 | 160 | 0 | 0 | 130 | 250 | 0 | 0 | 0 | 0 | 11700 | 20800 | 0 | 0 | 32500
Series 5 Pump | Program Mgmt | Project Manager | 60 | 80 | 80 | 60 | 60 | 60 | 0 | 0 | 145 | 400 | 8700 | 11600 | 11600 | 8700 | 8700 | 8700 | 0 | 0 | 58000
|  | TOTAL | 820 | 1200 | 1480 | 1050 | 570 | 370 | 0 | 0 |  | 5490 | 107400 | 145200 | 175200 | 132150 | 76300 | 50350 | 0 | 0 | 686600

## Expenses
Expenses
Travel, capital, outside services and direct purchases — by phase, by quarter.
Project | Phase | Category | Q1 2026 $ | Q2 2026 $ | Q3 2026 $ | Q4 2026 $ | Q1 2027 $ | Q2 2027 $ | Q3 2027 $ | Q4 2027 $ | Total $
Series 7 Coolant Pump | Design | Direct Purchases | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
Series 7 Coolant Pump | Prototype Build | Capital | 0 | 45000 | 15000 | 0 | 0 | 0 | 0 | 0 | 60000
Series 7 Coolant Pump | Validation Testing | Outside Services | 0 | 0 | 22000 | 12000 | 0 | 0 | 0 | 0 | 34000
Series 7 Coolant Pump | Qualification | Travel | 0 | 0 | 0 | 6000 | 4000 | 0 | 0 | 0 | 10000
Series 5 Pump | Design Update | Direct Purchases | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
Series 5 Pump | Validation Testing | Outside Services | 0 | 15000 | 18000 | 0 | 0 | 0 | 0 | 0 | 33000
Series 5 Pump | Production Readiness | Capital | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000
Series 5 Pump | Field Trial | Travel | 0 | 0 | 0 | 0 | 5000 | 7000 | 0 | 0 | 12000
|  | TOTAL | 13000 | 60000 | 85000 | 18000 | 9000 | 7000 | 0 | 0 | 192000

## Summary
Annual Planning Summary
Time-phased cost & FTE by quarter, a scenario view, and totals by project — all pulled from the tabs.
Metric | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Total
Labor Cost ($) | 107400 | 145200 | 175200 | 132150 | 76300 | 50350 | 0 | 0 | 686600
Expense Cost ($) | 13000 | 60000 | 85000 | 18000 | 9000 | 7000 | 0 | 0 | 192000
Total Cost ($) | 120400 | 205200 | 260200 | 150150 | 85300 | 57350 | 0 | 0 | 878600
Contingency ($) | 12040 | 20520 | 26020 | 15015 | 8530 | 5735 | 0 | 0 | 87860
Total + Contingency ($) | 132440 | 225720 | 286220 | 165165 | 93830 | 63085 | 0 | 0 | 966460
Labor Hours | 820 | 1200 | 1480 | 1050 | 570 | 370 | 0 | 0 | 5490
FTE (avg in quarter) | 1.9712 | 2.8846 | 3.5577 | 2.524 | 1.3702 | 0.88942 | 0 | 0 | 3.2993
Scenario view
Multipliers applied to Total + Contingency. A single blunt multiplier is a rough proxy — PlanX runs full optimistic / expected / pessimistic input sets through the same engine, so each scenario traces to the specific assumptions that changed.
Scenario | Multiplier | Total Cost ($)
Optimistic | 0.9 | 869814
Expected | 1 | 966460
Pessimistic | 1.15 | 1111429
Total cost by project
Project | Labor ($) | Expense ($) | Total ($)
Series 7 Coolant Pump | 438150 | 112000 | 550150
Series 5 Pump | 248450 | 80000 | 328450
Get PlanX → planxpm.com
Note on J12: Total column is FTE-years (total hours ÷ annual hours per FTE).